## Sheet1
Consumption
Service Name | Name, First Name | Job Role | 1. 01.2018 - 14.01.2018 | 15.01.2018 - 14.02.2018 | Consumed PD | Summary of work - 01.01.2018 - 14.01.2018 | Details of work - 01.01.2018 - 14.01.2018 | Summary of work - 15.01.2018 - 14.02.2018 | Details of work - 15.01.2018 - 14.02.2018
Systems Integration Services |  | Put your Role here | 20 | 44 | 64
Service Area : ADAMS - SHSDB Lead Name : Harish | Sudipta Sen Sarma | HP/ALM Developer / Test Specialist | 10 | 22 | 32 | - Support in System Functional testing (in the SAPBO, Java UI and Regression area) - Environment setup to work from inside the ODC | - Received Citrix account ID, set up account and raised request for necessary VM, tools and applications -Had brief understanding session with Amit on SHSDB application - Supported System testing for iteration 2 release for SHSDB application - Executed approx 12 Functional Test cases from JAVA UI and SAP BO test suite | - Powershell POC - Automation of SHSDB Functional Test Cases - Component Assessment for SHSDB Automation - Automation of SHSDB Technical Test Cases - Knowledge Transfer | - Did technology assessment for technical test suite to be automated - Worked on powershell automation POC. It was a part of technical test set automation feasibility check - Worked on Database related test cases to check feasibility using HP UFT API test - Did component assessment for SHSDB test cases automation - Worked on Automation of 4 functional test cases - Had 5 KT sessions from Amit from functional end of SHSDB application - Had 5 KT sessions from Harish from automation end and automation tools used in ECB
Service Area : ADAMS - SHSDB Lead Name : Harish | Swati Gupta | HP/ALM Developer / Test Specialist | 10 | 22 | 32 | -Supported function testing for SHSDB iteration 2 release(ADAMS project) -Supported CASPER UI testing -Environment setup to work from inside the ODC -Automation script execution to test accessibility from ODC | ADAMS: - Received Citrix account ID, set up account and raised request for necessary VM, tools and applications -Had brief understanding session with Amit on SHSDB application - Supported System testing for iteration 2 release for SHSDB application - Executed approx 12 Functional Test cases from JAVA UI and SAP BO test suite - Run a sample automation script to check accessibility from ODC and shared the evidence with onshore CASPER: - Supported UI testing from ODC for CASPER screens | - Powershell Automation POC - Automation of SHSDB Functional Test Cases - Component Assessment for SHSDB Automation - Automation of SHSDB Technical Test Cases - Knowledge Transfer from Onshore leads - Demonstration of Automated Test cases to Onshore manager | - Did technology assessment for technical test suite to be automated - Worked on powershell automation POC. It was a part of technical test set automation feasibility check - Worked on Database related test cases to check feasibility using HP UFT API test - Did component assessment for SHSDB test cases automation - Worked on Automation of 4 functional test cases - Demonstrated automation work to Onshore Lead and Manager - Had 5 KT sessions from Amit from functional end of SHSDB application - Had 5 KT sessions from Harish from automation end and automation tools used in ECB

## Sheet3
Made some changes to test git

## Sheet2
1-14 Jan Summary | Details
- Support in System Functional testing (in the SAPBO, Java UI and Regression area) - Environment setup to work from inside the ODC | - Received Citrix account ID, set up account and raised request for necessary VM, tools and applications -Had brief understanding session with Amit on SHSDB application - Supported System testing for iteration 2 release for SHSDB application - Executed approx 12 Functional Test cases from JAVA UI and SAP BO test suite
15jan-14feb Summary | Details
- Powershell POC - Automation of SHSDB Functional Test Cases - Component Assessment for SHSDB Automation - Automation of SHSDB Technical Test Cases - Knowledge Transfer | - Did technology assessment for technical test suite to be automated - Worked on powershell automation POC. It was a part of technical test set automation feasibility check - Worked on Database related test cases to check feasibility using HP UFT API test - Did component assessment for SHSDB test cases automation - Worked on Automation of 4 functional test cases - Had 5 KT sessions from Amit from functional end of SHSDB application - Had 5 KT sessions from Harish from automation end and automation tools used in ECB